| LISKEARD NEIGHBOURHOOD PLAN TEAM Meeting No. 10 |
| --- |
| NOTES |
| MEETING DATE: 8/9/2014 | MEETING VENUE: Quimperle Room, Public Hall. |
| PRESENT: James Shrubsole, Lorna Shrubsole, Rachel Brooks, Jane Pascoe, Roger Holmes, Steve Besford-Foster, Stephen Vinson, Susan Shand. Apologies: Sally Hawken, Sue Pike |
| NO. | ITEM. |
| 1. | Declarations of Interest None |
| 2. | Notes of Last Meeting and Matters Arising Both local Newspapers had good coverage of the LNP consultation. |
| 3. | Community Engagement Meeting for volunteers happened on 30th July 2014. JS, SB-F and Zoe Bernard-John established effective communication links with Menheniot NP Team and Parish Council. Assistance given towards their NP. It was agreed that there would be regular update meetings and co-operation over future developments. Suggested Farmers Breakfast unable to go ahead due to harvest activities but NFU contacted farmers by letter encouraging input to NP. SH attended Mother's group. LS Attended Morley Tamblin and Passmore Edwards. Business Breakfast well attended. Feedback from Business community good with ideas and support offered. Surveys: 576 surveys received and entered on Survey Monkey. Sample amounts to 6% of the population of Liskeard and 12% of all households. Gender mix balanced at 57% female 43% male. Good gender/age balance for the sample. (see additional graphs) |
| 4. | Budget update & Locality grant application Locality Grant received £4250.00 for 2014/15. Short time-scale requires close monitoring. SB-F provided provisional budgets up to 2016. A number of items flagged up the future need for additional funding. Additional grant sources to be investigated. |
| 5. | Project Plan Review – Planning the next steps Now half way through the plan. Next steps: build the evidence base establish sub-groups. |
| 6. | Briefing Consultants SB-F Reported contact with Plymouth University Business School towards a PHD Student to do statistical analysis on the data from surveys. To liaise and prepare brief. ACTION: SB-F Preparation of evidence base by similar means ? Research faculty and Supervisor possibilities, or employ consultant? Plus possible input from NP team? ACTION: SB-F |
| 7. | Briefing Sub-Groups Write Principles and Policy for the sub-groups in draft brief. ACTION: SB-F |
| 8. | Volunteer evening feedback and Recruitment Write and circulate Press Release for volunteers for working groups ACTION: JS & SB-F Contact details for potential chairs to JS. JS to co-ordinate. ACTION: JS Plan Volunteer evening |
| 9 | AOB None noted |
| 10 | Notes of actions agreed Feedback press release on consultation and asking volunteers to come forward by contact with Town Council/website. ACTION: JS, SB-F & SV Respond to Plymouth Business School re analysis and enquire re evidence base work. ACTION: SB-F Working Groups x 4. Potential candidates for chairs co-ordinate and discuss. ACTION: SB-F & JS Analysis of survey results. ACTION: JS, RB, SB-F, PLYM Bus School. Filing space needed in office. ACTION: SV to create space. Prepare brief for 4 groups: ACTION: SB-F with JS Link FB to Website PDF of survey graphs and date enter on website. ACTION: SB-F |
| 11 | Recommendations to Town Council Verbal report on progress and receipt of grant aid to full council next week. ACTION: JS |
| 12 | Next Meetings 6 October 3 November 1 December |