|  |
| --- |
| Item 2: Notes of Last Meeting**LISKEARD NEIGHBOURHOOD PLAN TEAM Meeting No. 9** |
| **NOTES** |
| **MEETING DATE:** 14/07/2014 | **MEETING VENUE:** Quimperle Room Public Hall, Liskeard |
| PRESENT: James Shrubsole, Lorna Shrubsole, Sally Hawken, Jane Pascoe, Roger Holmes, Steve Beresford-Foster. Apols from Rachel Brooks, Susan Shand, Sue Pike. |
| **NO.** | **ITEM.** |
| 1. | **Declarations of Interest**NONE |
| 2. | **Notes of Last Meeting and Matters Arising** NONE  |
| 3.  | **Project Plan Review**Brief review showed that project was on target but some rearrangement of sequence necessary to accommodate extended community engagement period. |
| 4. | **Budget position**Noted that project operating within draft budget at present. SBF to put together bid for Locality grant. |
| 5. | **Forthcoming Community Engagement**Arrangements Staffing arrangements for the community events, exhibitions and press announcements were agreed. It was agreed that the closedown for comments was 1st August and a press release announcing this would be prepared.  |
|  | **Update on Neighbourhood Plans**SBF gave an update on the latest developments nationally involving Neighbourhood Plans. |
| 6. | **AOB**Volunteers evening – noted that this event on 31st August did not require full team attendance and would be handled by James and Steve. |
| 7. | **Notes of actions agreed**SBF to put together bid for Locality grant.Agreed that the closedown for comments was 1st August and a press release announcing this would be prepared.  |
| 8. | **Recommendations to Town Council** NONE |