## Sheet1
Liskeard NP Project Plan - Edition 5. October 2014
Stages | Action | Activities | Progress | How long? | When? | [31 empty] | Notes
[5 empty] | 2013 |  | 2014 | [11 empty] | 2015 | [11 empty] | 2016
[5 empty] | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Stage 1: Starting up | Getting started: Town Council Authority | Town Council meet to discuss/agree potential Neighbourhood Plan e.g. process, ideas, aspirations | [34 empty] | Decision to include allocations included. | bar: 2013 Nov; 2014 Mar
| Defining the Neighbourhood | Discuss the options and implications and a suggested Neighbourhood Plan Area | bar: 2013 Nov
Ensure that aims and objectives of doing the Neighbourhood Plan are clear/understood. | bar: 2014 Jan to 2014 Mar
| Submission of letter & map to Cornwall Council | Parish/Town Council to send letter and map to Cornwall Council to formally apply for Neighbourhood Area |  | 8 - 10 weeks (as 6 week consultation period) | bar: 2013 Nov
Parish/Town Council to suggest where CC might advertise Neighbourhood Plan locally (to reach those who live/work/have businesses in area) | bar: 2013 Nov
|  | Cornwall Council formally advertise Neighbourhood Area | [34 empty] | Closing date 7th Feb 2014 | bar: 2014 Jan to 2014 Feb
Cornwall Council decision following consultation period | bar: 2014 Apr
Stage 2: Ensuring community support for the neighbourhood planning process | Community Awareness Raising | Do pre-publicity/awareness raising with Town residents - ensuring they know what is being discussed - to parallel CC Advertisement | [34 empty] | Item on Liskeard FM, presentation at 2 Town Forum meetings, Press release, TC Website. | bar: 2013 Dec to 2014 Feb
Stage 3: Organising management of Plan | Set up Steering Group / Neighbourhood Planning Team | Set up Neighbourhood Plan Team and agree roles (chair etc) | bar: 2013 Nov; 2014 Jan
Agree roles within Neighbourhood Plan Team | bar: 2014 Jan
Establish Neighbourhood Plan Team Terms of Reference and agree with Town Council as 'Qualifying Body' providing for appropriate authoritity to act. | bar: 2013 Dec to 2014 Jan
Agree and set up process to ensure flow of information between Parish/Town Council Clerk and Neighbourhood Plan Team | bar: 2014 Jan
Neighbourhood Plan team Meetings meetings (monthly) | bar: 2013 Dec to 2014 Apr
Appoint note taker for Steering Group
Consider if Steering Group would benefit from other representation | bar: 2014 Jun
Consider Skills / knowledge of Neighbourhood Plan Team and recruit additional members to strengthen if appropriate | bar: 2014 Jun
Consider links with and role of Town Forum and Town Team in process | bar: 2014 Jun
Check for inclusivity and diversity in the makeup of the Steering Group | bar: 2014 Jun
Set up initial task and finish 'working groups' - (1) Project Planning (2) Engagement | bar: 2013 Nov
Set up pool of volunteers and support with volunteer evenings etc. | bar: 2014 Mar to 2014 May; 2014 Aug; 2014 Nov; 2015 Feb; 2015 May; 2015 Aug; 2015 Nov; 2016 Feb
| Develop and keep under review Project Plan | Appointment of Project Manager. | bar: 2013 Dec to 2014 Jan
Populate Action Plan with time scales (for tasks & realistic timeframe for process) & resources (people/funding) etc. | bar: 2014 Jan to 2014 Feb
Agree Project Plan | bar: 2014 Jan to 2014 Feb
| Assess and keep under review the budget requirement | Realistic assesment of budget needs, will need to be reviewed as plan content emerges and further studies required, | bar: 2014 Mar
| Secure funding | Apply for DCLG/CC support | bar: 2014 Jun to 2014 Aug
Apply for Liskeard TC funding | bar: 2014 Mar to 2014 Apr
Apply for CC Community Chest support | bar: 2014 Jan to 2014 Mar; 2014 Nov to 2014 Dec
Set up and maintain budget management process. | bar: 2014 Jan
Stage 4: Developing communication and engagement strategy | Understand nature of area, demographic, key stakeholders, accesibilty needs etc. | Identify key partners and stakeholders including potential developers and landowners | bar: 2014 Oct to 2014 Dec
Develop and agree communication and engagement strategy (what/who/how/when/why) | bar: 2014 Feb to 2014 Apr
Ensure that process includes provision for revalidation of findings from previous Liskeard strategies. | bar: 2014 May to 2014 Jul
Establish project's visual identity | bar: 2014 Feb to 2014 Mar
Set up website, Facebook and Twitter accounts | bar: 2014 Mar to 2014 Apr
Ensure that strategy is inclusive and accessible to all, includes provision for CIA, and covers entire Plan development process. | bar: 2014 Feb
Stage 5: Raising community awareness ('FRONT LOADING') and engagement in Neighbourhood Plan process; identifying community priorities. | Community Engagement Activity | Information/awareness raising community events and outline questionnaire (based on communication and engagement strategy) | bar: 2014 May to 2014 Aug
Engage with local groups and people to gain their views on doing the neighbourhood plan, area, local issues and priorities | bar: 2014 May to 2014 Aug
Ensure events and questionnaire are inclusive by checking back to Engagement Strategy | bar: 2014 May to 2014 Aug
Analyse questionnaire responses; gauge support and understanding of neighbourhood planning; broadly define key issues and community priorities from responses | bar: 2014 Sep to 2014 Nov
Update Engagement Strategy; begin compiling consultation statement | bar: 2014 Jun; 2014 Oct to 2014 Nov; 2015 Jul; 2015 Oct
Publicise early feedback results from the initial questionnaire/engagement | bar: 2014 Oct
Report on engagement results and community priorities to Town Council | bar: 2014 Nov
| Key Stakeholder Engagement | Carry out stakeholder identification session | bar: 2014 May; 2014 Oct
Establish what interest there is from potential developers/landowners | bar: 2014 Dec to 2015 Feb
Discussions with community interest groups | bar: 2014 Dec to 2015 Feb
Summarise stakeholder positions | bar: 2015 Feb
Ongoing liaison with key stakeholders | bar: 2014 Oct to 2016 Jun
Stage 6: Information gathering | Building the Evidence Base | Establish status of Liskeard Town Framework and other Cornwall Local Plan policies. | bar: 2014 Feb to 2014 Mar
Identify previous strategies and policy documents (eg Liskeard Community Strategic Plan) and assess what research and policy directions should be carried forward. | bar: 2014 Oct to 2014 Dec
Identify other Town Council policies, proposals and 'interventions' that need land-use support. | bar: 2014 Oct to 2014 Dec
Gather existing information e.g. demographic and socio-economic information, designated/protected sites, views from the initial questionnaire and community events | bar: 2014 May to 2014 Dec
Assess evidence gathered to identify gaps | bar: 2014 Jul to 2014 Oct
Establish what evidence is still required and where it may be sourced | bar: 2014 Oct
Source or produce additional evidence if required | bar: 2014 Oct to 2014 Dec
Undertake mapping exericise - e.g. infrastructure, trees and environmental elements, leisure facilities, shops, historical assets etc (THIS MAY BE DONE BY WORKING GROUPS - SEE BELOW) | bar: 2014 Oct to 2015 Jan
Review relevent local and national planning policies and guidance | bar: 2014 Oct to 2014 Dec
Undertake analysis of evidence; prepare report of findings. | bar: 2014 Oct to 2014 Dec; 2015 Oct
Report to Town Council on Findings | bar: 2015 Jan to 2015 Feb
Stage 7 Pulling community engegement results and evidence together | Define scope, strategic vision and aims, outline content, thematic objectives and options; in-depth community and stakeholder involvement | FACILITATED NEIGHBOURHOOD PLAN TEAM EVENT to develop draft vision, aims, key theme objectives and issues for the Neighbourhood Plan. | bar: 2014 Nov to 2014 Dec
Report on draft vision etc to Town Council | bar: 2015 Jan to 2015 Feb
ESTABLISH WORKING GROUPS to examine development and policy options in context of baseline information and public opinion | bar: 2014 Oct
Identify optional opportunity sites for development and valuable community spaces for protection. | bar: 2014 Nov to 2015 Jan
WGs hold community or interest group events and in-depth surveys to investigate and explore various policy and development options | bar: 2014 Dec to 2015 Feb
WGs formulate policy and propsal strategies for each theme, ensuring that they relate to other Town Council policies and proposals. | bar: 2015 Jan to 2015 Feb
WGs Review against relevant local and national planning policies and guidance | bar: 2015 Feb
WORKING GROUPS REPORT and Neighbourhood Plan Team draws up outline draft strategy and plan. | bar: 2015 Feb
Seek advice from Cornwall Council on assessments that may be required, e.g. Strategic Environmental Assessment (early 'Scoping Opinion' on SEA), Habitats Regulations Assessment, Environmental Impact Assessment, flood risk assessment etc | bar: 2015 Feb
Outline Draft Strategy and Plan Recommendations to Town Council | bar: 2015 Mar
TOWN COUNCIL CONFIRM outline of content and policy directions | bar: 2015 Mar
Commision assements where necessary. | bar: 2015 Mar to 2015 May
Inform landowners/developers; secure agreement on preferred Plan direction. | bar: 2015 Mar to 2015 May
Stage 8: Narrowing down the options and technical writing of draft plan. | Technical writing and sign off by Town Council. | Neighbourhood Plan Team training on planning policy writing. | bar: 2015 Mar
Appoint consultants for technical writing if approriate. | bar: 2015 Mar to 2015 Apr
Decide plan layout, format, design etc | bar: 2015 Apr
Draft planning policies and proposals | bar: 2015 Apr to 2015 May
Carry out sustainability check of draft policies and proposals; consider mitigation measures to alleviate negative impacts and maximise positive outcomes; prepare sustainablity statement. | bar: 2015 May
Seek 'Scoping Opinion' from Cornwall Council as to whether Strategic Environmental Appraisal is necessary. | bar: 2015 May
Do 'rural proofing' assessment of draft policies and proposals. | bar: 2015 May
Do Equality Impact Assesment of draft policies and proposals | bar: 2015 May
Do 'Basic Conditions' check to ensure plan is 'fit for purpose' within terms of the Act and Regs; prepare 1st draft Basic Conditions Statement | bar: 2015 May
Make changes to draft policies and proposals in light of above checks | bar: 2015 May
Check conformity with Cornwall Council's Local Plan | bar: 2015 May
Compile draft Neighbourhood Plan document and maps | bar: 2015 Jun
TOWN COUNCIL 'SIGN-OFF' | bar: 2015 Jun
Make any amendments consequent to sign-off. | bar: 2015 Jul
Review engagement strategy. | bar: 2015 Jul
Proofread draft Neighbourhood Plan | bar: 2015 Jul
Finalise draft Neighbourhood Plan for publication and formal six-week consultation (see below) | bar: 2015 Jul
Stage 9 : Testing and approving the Neighbourhood Plan | Pre-submission Consultation | PUBLISH AND CONSULT ON DRAFT NEIGHBOURHOOD PLAN to ensure it represents what the community want - also feedback on results from earlier engagement and consultation and demonstrate how the Neighbourhood Plan tackles the issues raised. |  | Minimum 6 week period | bar: 2015 Aug to 2015 Sep; 2016 Feb to 2016 Mar
| Finalise Plan | Town council to make any amendments necessary following pre-submission consultation. NOTE THAT SIGNIFICANT CHANGES MAY REQUIRE FURTHER PRE-SUBMISSION CONSULTATION. | bar: 2015 Oct; 2016 Mar to 2016 Apr
Re-check Plan against various assessments as necessary | bar: 2015 Oct; 2016 Mar to 2016 Apr
Re-check Plan for general conformity with Cornwall Council's Local Plan | bar: 2015 Oct; 2016 Mar to 2016 Apr
Prepare Basic Conditions Statement | bar: 2015 Oct; 2016 Mar to 2016 Apr
Finalise evidence summary | bar: 2015 Oct; 2016 Mar to 2016 Apr
Finalise Consultation Statement | bar: 2015 Oct; 2016 Mar to 2016 Apr
| Submission of Plan & Approval | SUBMIT THE NEIGHBOURHOOD PLAN TO CORNWALL COUNCIL This must include the draft Neighbourhood Plan statement, the Neigbourhood Plan map and statement identifying the area, Consultation Statement, Basic Conditions Statement, Strategic Environmental Assesment (or CC Screening Opinion), copies of any other assessments required, and a summary of the evidence that supports the Plan policies and proposals. |  | Approximately 26 - 40 weeks (due to 6 week consultation period on draft, 8 - 12 weeks for independent examination and 8 - 12 weeks to organise and hold referendum) | bar: 2015 Oct; 2016 Apr
Cornwall Council reviews the Neighbourhood Plan and if it meets requirements, it will then be formally publicised for consultation
Cornwall Council arrange for independent examination
EXAMINATION BY INDEPENDENT ASSESSOR
CC Considers Examiners recommendations in consultation with Parish/Town Council
Modify or not? ( Cornwall Council may make modifications to the Neighbourhood Plan before the referendum to ensure that it complies with the recommendations of the examiner's report)
If the Neighbourhood Plan has to be modified, details to be publicised
Stage 10: Plan id Made | Formal ‘Making’ of Plan as part of the planning policy framework. | REFERENDUM is organised by Cornwall Council
Legal process of ‘MAKING’ of plan (if all of the above is successful)
Stage 11: Delivering and monitoring the plan | Delivery | Town Council develop an Implementation Plan, e.g. linking with other Council policies and working with developers to make it happen
MONITORING - (1) of progress against objectives and reporting back to the community; (2) of implementation of Plan policies by Cornwall Council as the Local Planning Authority
Key:
Not Started - Late
In Progress - On Plan
Completed